## Template
Program Communications Plan Program: Employee Morale and Engagement Date and Version: (Date), Version 1
Communications Item | Item Owner | Target Audience | Media/Channels | Frequency | Purpose/Objective | Comments
Program Kick-Off Meeting | Program Manager | All stakeholders | In-person/Virtual meeting | Once at start | Introduce the program, objectives, key stakeholders, and timelines | Sets the stage for the program and aligns everyone on the program's goals
Weekly Status Updates | Program Manager | Program team, Stakeholders | Email | Weekly | Provide updates on program progress | Highlight milestones, risks, and issues
Monthly Progress Reports | Project Managers | Executive Team, HR Director | Report (PDF/Doc) | Monthly | Detailed progress report and performance metrics | Include detailed metrics and achievements
Wellness Program Announcements | Wellness Coordinator | Employees | Email, Intranet | Monthly | Inform about upcoming wellness activities | Provide schedule, content, and participation details
Recognition and Reward Announcements | Project Manager - Recognition | Employees | Email, Intranet | Monthly | Announce recognition and rewards for employees | Include award criteria, recipients, and ceremonies
Stakeholder Feedback Sessions | Communications Manager | All stakeholders | Workshops/Surveys | Quarterly | Gather feedback from stakeholders | Collect and analyze feedback for improvements
Executive Briefings | Program Manager | Executive Team | Presentation | Bi-monthly | High-level updates for executives | Summarize program progress and strategic alignment
Risk and Issue Logs | Program Manager | Program team, Stakeholders | Shared Document/Email | Ongoing | Communicate risks and issues | Maintain a log for transparency and mitigation
Health and Safety Updates | Health and Safety Officer | Employees | Email, Intranet | Every Two Weeks | Inform about health and safety measures | Provide updates on policies and improvements
Employee Survey Results | HR Analyst | Program team, Stakeholders | Report (PDF/Doc), Presentation | Quarterly | Summarize results of employee surveys on morale and engagement | Provide insights and action plans based on feedback
End-of-Phase Review Meetings | Program Manager | Program team, Stakeholders | In-person/Virtual meeting | End of each phase | Review accomplishments, lessons learned, and next steps | Ensure readiness for the subsequent phase
Recognition Program Reviews | Project Manager - Recognition | HR Director, Employees | Report (PDF/Doc), Meeting | Quarterly | Evaluate the effectiveness of the recognition and reward system | Gather feedback and make necessary adjustments
Wellness and Work-Life Balance Workshops | Wellness Coordinator | Employees | In-person/Virtual Workshops | Monthly | Promote wellness and work-life balance | Topics may include stress management, nutrition, and work-life integration
Program Closure Report | Program Manager | All stakeholders | Report (PDF/Doc) | End of program | Summarize the program outcomes | Provide a comprehensive overview at the program’s conclusion