## Solution
Program Communications Plan Program: Smart Retail Transformation Program Date and Version: 20xx Version 1
Communications Item | Item Owner | Target Audience | Media/Channels | Frequency | Purpose/Objective | Comments
Program Kick Off Meeting | Program Manager | All stakeholders | In-person/Video Conference | Once, at the start | Outline program objectives, introduce team members
Weekly Status Updates | Project Managers | Project Managers, Team Leads, Portfolio Manager | Email/Online Meeting | Weekly | Review progress, address issues, plan for the upcoming week
Monthly Steering Committee Meetings | Program Manager | Executive Sponsor, Program Manager, Project Managers, Portfolio Manager | In-person/Video Conference | Monthly | Review overall program progress, discuss major risks and issues, make strategic decisions
Bi-Weekly Team Meetings | Project Managers | Project Teams, Portfolio Manager | In-person/Online Meeting | Bi-weekly | Discuss detailed project progress, solve problems, ensure alignment
Ad Hoc Issue Resolution Meetings | Relevant Stakeholders | Relevant Stakeholders | In-person/Online Meeting | As needed | Address urgent issues or decisions that cannot wait for regular meetings
Quarterly Progress Reports | Program Manager | All Stakeholders | Email/Online Report | Quarterly | Provide comprehensive updates on program progress, highlight achievements, outline next steps
Customer Feedback Surveys | Marketing Team | Customers | Online Survey | Periodically after major milestones | Gather feedback on new systems and features to inform improvements
End-of-Phase Review Meetings | Program Manager | All Stakeholders | In-person/Online Meeting | At the end of each project phase | Evaluate completed phase, discuss lessons learned, plan for the next phase
Final Program Review | Program Manager | All Stakeholders | In-person/Video Conference | At program completion | Review overall program outcomes, celebrate successes, document lessons learned