## Solution
Resource Breakdown Structure Program: Smart Retail Transformation Program Date and Version: 20xx, Version 1
Program Objective:
Program Component | Resource Requirement | Resource Cost | Resource Source | Schedule (Start) | Schedule ( End) | Dependencies | Priority
AI-Powered Inventory Management | Data Scientists, IT Team, Inventory Managers | 525000 | Internal and External | Q1 20XX | Q2 20XX | Existing inventory systems integration | High
Smart Checkout System | Software Developers, Security Team, Retail Staff | 400000 | Internal | Q2 20XX | Q3 20XX | Mobile app integration | High
Customer Engagement App | App Developers, Marketing Team, Customer Service Team | 300000 | Internal | Q1 20XX | Q3 20XX | AI recommendations integration | Medium
Enhanced Security System | Security Experts, IT Team, Store Managers | 350000 | Internal and External | Q3 20XX | Q4 20XX | Real-time monitoring systems | Medium
External Training Component | External training vendor, all project team members | 200000 | External | Q1 20XX | Q4 20XX | Successful completion of training | High
Total Program Costs |  | 1775000
Explanation of Columns Program Component: The main project or component of the program. Resource Requirement: Specific resources needed to accomplish the component. Resource Cost: The cost associated with each resource requirement. Resource Source: Where the resource will be obtained (internal, external vendor, etc.). Schedule (Start): The start date for when the resource will be needed. Schedule (End): The end date for when the resource will no longer be needed. Dependencies: Any dependencies that must be addressed before the resource can be utilized. Priority: The priority level of the resource (High, Medium, Low).