## Template
Resource Breakdown Structure Program: Date and Version:
Program Objective:
Program Component | Resource Requirement | Resource Cost | Resource Source | Schedule (Start) | Schedule ( End) | Dependencies | Priority
Total Program Costs
Explanation of Columns Program Component: The main project or component of the program. Resource Requirement: Specific resources needed to accomplish the component. Resource Cost: The cost associated with each resource requirement. Resource Source: Where the resource will be obtained (internal, external vendor, etc.). Schedule (Start): The start date for when the resource will be needed. Schedule (End): The end date for when the resource will no longer be needed. Dependencies: Any dependencies that must be addressed before the resource can be utilized. Priority: The priority level of the resource (High, Medium, Low).

## Example
Resource Breakdown Structure Program: Inventory Management System Upgrade Program Date and Version: 08/01/20xx Version 1
Program Objective: To modernize the inventory management system and revamp the inventory warehouse to enhance operational efficiency and improve overall performance at Sakura Sweets LLC. This includes comprehensive training for staff to ensure smooth implementation and usage of the new system.
Program Component | Resource Requirement | Resource Cost | Resource Source | Schedule (Start) | Schedule ( End) | Dependencies | Priority
Training Development | Trainers | 10000 | External Vendor | 20xx-08-01 | 20xx-08-31 | Approval from HR | High
| Training Materials | 5000 | Internal | 20xx-08-01 | 20xx-08-15 | Selection of Trainers | High
New Inventory System | Software Licenses | 50000 | Software Vendor | 20xx-09-01 | 20xx-09-30 | Budget Approval | Medium
| Implementation Team | 100000 | Internal Team | 20xx-09-01 | 20xx-12-31 | Completion of Training | High
Warehouse Revamp | Construction Workers | 200000 | Construction Co. | 20xx-10-01 | 20xx-02-28 | Finalized Design Plans | Medium
| Equipment | 50000 | Equipment Vendor | 20xx-10-01 | 20xx-11-30 | None | Low
Barista Performance | Barista Trainers | 30000 | External Vendor | 20xx-11-01 | 20xx-11-30 | Availability of Venue | Medium
| Training Venue | 5000 | Rental Company | 20xx-11-01 | 20xx-11-30 | None | Medium
Total Program Costs |  | 450000
Explanation of Columns Program Component: The main project or component of the program. Resource Requirement: Specific resources needed to accomplish the component. Resource Cost: The cost associated with each resource requirement. Resource Source: Where the resource will be obtained (internal, external vendor, etc.). Schedule (Start): The start date for when the resource will be needed. Schedule (End): The end date for when the resource will no longer be needed. Dependencies: Any dependencies that must be addressed before the resource can be utilized. Priority: The priority level of the resource (High, Medium, Low).