## Template
Resource Breakdown Structure Program: Java Delight Expansion Program Date and Version: 15 Jul 20xx Version 1
Program Objective: As part of its expansion plan, Java Delight identified several key areas that require improvement to maintain its competitive edge and ensure smooth operations across all locations. The primary focus areas are upgrading the inventory management system, revamping the central warehouse, improving barista performance, and developing comprehensive staff training programs.
Program Component | Resource Requirement | Resource Cost | Resource Source | Schedule (Start) | Schedule ( End) | Dependencies | Priority
Barista Training Development | Trainers | 15000 | External Vendor | 20xx-08-01 | 20xx-08-31 | Approval from HR | High
| Training Materials | 5000 | Internal | 20xx-08-01 | 20xx-08-31 | Selection of Trainers | High
New Inventory System | Software Licenses | 60000 | Software Vendor | 20xx-09-01 | 20xx-09-30 | Budget Approval | Medium
| Implementation Team | 80000 | Internal Team | 20xx-09-01 | 20xx-12-31 | Completion of Training | High
Warehouse Revamp | Construction Workers | 180000 | Construction Co. | 20xx-10-01 | 20xx-02-28 | Finalized Design Plans | Medium
| Equipment | 65000 | Equipment Vendor | 20xx-10-01 | 20xx-11-30 | Timely Delivery | Medium
Staff Development | Trainers | 10000 | External Vendor | 20xx-08-01 | 20xx-08-31 | Selection of Trainers | High
| Training Materials | 5000 | Internally | 20xx-08-01 | 20xx-08-31 | Approval from HR | High
Total Program Costs |  | 420000
Explanation of Columns Program Component: The main project or component of the program. Resource Requirement: Specific resources needed to accomplish the component. Resource Cost: The cost associated with each resource requirement. Resource Source: Where the resource will be obtained (internal, external vendor, etc.). Schedule (Start): The start date for when the resource will be needed. Schedule (End): The end date for when the resource will no longer be needed. Dependencies: Any dependencies that must be addressed before the resource can be utilized. Priority: The priority level of the resource (High, Medium, Low).