## Solution
Program Stakeholder Register Program: Smart Retail Transformation Program Date and Version: 20xx, Version 1
Position | Name | Organization | Component Supported | Role Description | R: Responsible | A: Accountable | C: Consulted | I:Informed | Required Timeframe | Comments
Portfolio Manager | Priya Sanders | Portfolio Management Office (PMO) | Entire Program | Ensure alignment with strategic objectives |  | X |  | X | Throughout the program | Regular status meetings
Executive Sponsor | David Lee | Senior Leadership Team | Entire Program | Provide high-level oversight and support |  | X |  | X | Throughout the program | Steering committee meetings
Program Manager | Robert Kumar | Program Management Office (PMO) | Entire Program | Oversee program, manage resources and risks | X |  |  | X | Throughout the program | Weekly updates
Project Manager | To Be Determined | Program Management Office (PMO) | Individual Projects | Lead project execution, manage team | X |  |  |  | Throughout the project | Daily stand-ups
Data Scientists | To Be Determined | Data Analytics Department | AI-Powered Inventory Management | Develop and test AI algorithms | X |  |  |  | Project duration | Technical meetings
IT Team | To Be Determined | Information Technology Department | All Projects | Integrate systems, ensure technical support | X |  |  |  | Throughout the project | Technical meetings, integration plans
Inventory Managers | To Be Determined | Supply Chain Management | AI-Powered Inventory Management | Validate AI predictions, manage inventory |  |  | X |  | Project duration | Review meetings, feedback sessions
Vendors/Suppliers | To Be Determined | External Partners | AI-Powered Inventory Management | Supply goods and services | X |  |  |  | Project duration | Contract agreements, regular communication
Software Developers | To Be Determined | Information Technology Department | Smart Checkout System, Engagement App | Develop self-checkout and app software | X |  |  |  | Project duration | Agile sprints, code reviews
Security Team | To Be Determined | Security Department | Smart Checkout System, Security System | Implement fraud detection, surveillance | X |  |  |  | Project duration | Security audits, regular updates
Retail Staff | To Be Determined | Store Operations | Smart Checkout System | Provide user feedback, ensure usability |  |  | X |  | Project duration | Training sessions, feedback loops
Customers | To Be Determined | N/A (External) | Smart Checkout System, Engagement App | Use new systems, provide feedback |  |  |  | X | Project duration | Customer surveys, feedback channels
App Developers | To Be Determined | Information Technology Department | Customer Engagement App | Develop and maintain customer engagement app | X |  |  |  | Project duration | Agile sprints, User feedback integration
Marketing Team | To Be Determined | Marketing Department | Engagement App | Manage loyalty programs, promotions |  |  | X |  | Project duration | Campaign planning, performance reports
Customer Service Team | To Be Determined | Customer Support Department | Engagement App | Support app users, manage queries |  |  | X |  | Project duration | Training, regular updates
Security Experts | To Be Determined | Security Department | Enhanced Security System | Develop security solutions | X |  |  |  | Project duration | Security briefings, regular updates
Store Managers | To Be Determined | Store Operations | Enhanced Security System | Monitor security systems, report issues |  |  | X |  | Project duration | Review meetings, feedback sessions
Employees | To Be Determined | N/A (Internal) | Enhanced Security System | Adapt to new security measures |  |  |  | X | Project duration | Training sessions, feedback channels
External Training Vendor | To Be Determined | External Partners | All Projects | Provide training across projects | X |  |  |  | Throughout the project | Training schedules, feedback reports
RACI Terms Defined | ROLE | DEFINED
| R | Responsible for performing work or tasks
| A | Accountable for outcomes
| C | Consult as a Subject Matter Expert (SME)
| I | Inform as project progresses