## Solution
Benefits Register Program Name: Java Delight Enhancement Program Date and Version: Version 1, 20 Nov 20xx
Identifier | Benefits Definition |  |  |  |  | Benefits Measurement Plan |  |  | Risk Management |  |  | Benefits Status |  | Actual Results
Benefit ID | Benefit Description | Program Component | Benefit Category | Benefit Owner | Projected Benefit Realization Target Date | Key Performance Indicators | Baseline | Target | Risk Assessment (H,M,L) | Probability of Achievement (1 (Low) to 5 (High) | Mitigation | Review Frequency | Planned/Started/Pending/ Complete/Delayed | Planned Versus Actual Benefits Realization
001 | Increased Customer Satisfaction | Customer App | Customer Satisfaction | App Development Team | Q3: Months 7-9 | User Satisfaction Survey | 70% Satisfied Users | 90% Satisfied Users | M | 4 | Regular updates and bug fixes | Monthly | Started | Pending
002 | Higher On-Line Sales | Website Upgrade | Operational Efficiency | Marketing Team | Q4: Months 10-12 | On-line Sales Reports | $50,000 Monthly Sales | $75,000 Monthly Sales | M | 3 | Continuous website optimization and user feedback integration | Quarterly | Started | Pending
003 | Improved Service Quality | Barista Performance | Operational Efficiency | Training Department | Q2: Months 3-6 | Customer Feedback and Metrics | Average Service Time 5 Minutes | Average Service Time 3 Minutes | L | 4 | Ensure all baristas complete training Provide on-going training support and refresher training | Monthly | Started | Pending